## Daily Report
Daily Status Report 04 Dec 2014
Developer Name | Project Name | Task Description | Current Status
Vikas Deshmukh | myct.in | Mhvidhan Mandal discussion and User log app work done | Completed
Ganesh Dhaybar | EzeeSchool | Fee Details web error resolve,Server database backup,ezeetest.in website transfer | in progress
Santosh Gurude | Myct.in(VidhanMandal) | Vidhan mandal web service get data in only one request | Completed
Pritam Kumbhar | EzeeDrug app | Work on GPs And Android Location Finder. | Completed
Tanaji Pochapure | VidhanMandal app | In vidhan mandal all web service are combine in one web service now only study completed not implimented yet | 93 %
Vinod Tarle | ezeePlanner app | birthday activity webservice sending data to server | 70% completed
Jitendra Patil | EzeeTest | work related server and study of RFP Real Estate | in progress
Amit Shinde | Practice | Drawing Polylines on Google Map | completed
Shweta Pingale | EzeePlanner | Do some validation part for all event for Drop down list,Date,change previous table update them | Completed

## Sheet1
Daily Status Report 12th Aug, 2013
Project Name | Developer Name | Task Description | Current Status | Completion Perc.(%)
myct.in | poonam | 1. create new class for exe store procedure . 2. create new class for send msg to all HM & All . 3. create new function manage hirarchy details. For use send mgs. 4. test msg is proper send or not. Check student total is correct or not | in progress | 90%
other | poonam | 1.check patil coding & help for new changes. 2. discus with shashank sir - how to get Student total . Solve msg problem with help sir. | completed | 99%
Online Exam | Atul | Add Medium and type of exam in in add question page and bind grid by class , medium , type of exam in subject, topic, Examname , add Question page ,create dependancy | completed | 100%
myct.in | ketan | 1.Work On Abstract table | completed | 100%
SchoolApp | vikas | Complet With permanent DB of State,Dist,city | completed | 100%
Create New web Pages | praveen kumar | Create new webpage for Address,paid,sample test web page change the content place and flash file uploded by the Dreamviewer banner logo and addd flash animation,index page added new part of naviagation DIV.Done the logo animation,Banner animation. | in progress | 50%
NSS | Padmaraj | nss coding with poonam madam, form of facilities to NSS | in progress | 90%
Daily Status Report 10th Aug, 2013
Project Name | Developer Name | Task Description | Current Status | Completion Perc.(%)
myct.in | poonam | 1. discus to shashank sir how to send all total 11 stage sms report. 2. mail to shashank sir Myct Database . & Details. 3. create dummy demo how to count all total. 3. create new table & user,his leader is,school code,mobile no for shashank sir requirment using send mes. | in progress | 50%
other | poonam | 1. get interview 2. discus with atul his problem. 3. help to patil related machine.config error try my end but not solve this problem. 4. call to sashikant panchal related server fillzill authority problm. 5. attend meeting with all emp & discus to dinesh sir related all project current Status. | in progress | 70%
Udisecce | ketan | 1.Add Modify Date To Student Presenty | Completed | 1.1%
myct.in | ketan | 1.Upload BJS PDF on online ,2. Work on Hirachy Report status With Mam, 3.Add table on Data base Archive School presenty | 1.Completed 2.In progess 3.completed | 1.100% _____ 3.100%
NSS | Padmaraj | tested Admin NSS, NSS MAC validation problem | in progress
SchoolApp | vikas | tested School app | in progress | 80%
Online Exam | Atul | Add type of exam and Medium in add Question page and Rechange all flow of subject page, add question page assign by Rina Mam | Completed | 100%
Create New web Pages | praveen kumar | Create new webpage for contact page,liveproject web page and change banner logo and addd flash animation,added some chnages address add in to there.. | in progress | 50%
Daily Status Report 9th Aug, 2013
Project Name | Developer Name | Task Description | Current Status | Completion Perc.(%)
Create New Web pages | praveen kumar | Created new web pages solve cross browser issues all pages check on different web browsers,and create new web page for paid final test. | in progress | 50%
myct.in | poonam | 1.completed displya Hirarchy report with person name, person role Name,Mobile No., School Code. 2. in progress all student presenty message sent to person. | 1. completed. 2. in progress | 1. 100% 2.30%
other | poonam | 1. Solve Atul coding problem. 2. get interview.
myct in | ketan | 1. Work on Hireachy report 2. Work on Aascii Page Dar Report | 1.In progress 2.In progress | 1.40% 2.50%
Udisecc | ketan | 1.Work on Dar Report 2. Student Presenty Report | in progress | _____
Online Exam | Atul | add two separate gridview in Examname pahe for Competative Exam and 1st to 10th standard and set chapter optional for cometative exam , same changes do for Chapter page and change coding and validation 2. add type of exam in question page | completed 2. inproress | 100% 2. 20%
SchoolApp | vikas | worked on data backup | in progress | 70%
NSS | Padmaraj | Lock, Deactive, Allow Changes and report done with testing on local side | in progress | 98%
Daily Status Report 8th Aug, 2013
Project Name | Developer Name | Task Description | Current Status | Completion Perc.(%)
myct.in | poonam | 1. Search how to generat Hirarchy report. 2. create hirarchy report demo on Local Side . 3. add new form displya hirarchy report. Check it proper or not. | in progress | 70%
server/domain | poonam | 1. create hosting space vishthamspm.in domain but fillzilla interface details not available so is pending. 2.mail to shashikant panchal. | in progress | 60%
other | poonam | 1. solve vikas apps problem my end remaining vikas end working. | completed | 99%
Udisecce | ketan | Add abstract School presenty table on myct Work Coding 1.DAR report 2.Student Presenty | completed | 100%
myctin | ketan | 1. ASCII report Add code of abstract School presenty table 2. Create event in myct Perticular time | 1.completed 2.In progress | 1.100% 2.40%
Online Exam | Atul | add new field select Medium, select exam type in table topic,subject,exam name and change database table And change dependancy of table subject,topic,exam name , add class table | Inprogress | 90%
NSS | Padmaraj | Nss Admin report and changes | completed | 95%
Create New Website | praveen kumar | Create new web page for paid test with some modify content on the index page added flash on the home page,create new page for mcqs test. | in progress | 50%
MemberApp | Vikas | Worked on WebService | Inprogress | 70%
Daily Status Report 7th Aug, 2013
Project Name | Developer Name | Task Description | Current Status | Completion Perc.(%)
myct.in | poonam | 1. Change coding AddnewUser.aspx page - bcoz if you modify that time reference not updated only role update. 2. Add Juniors coding completed with sub level & Some Level with 11 reference. 3. Search how to displya report with proper hirarchy | 1/2 -completed 3- in progress | 1/2- 100% 3-30%
Server/Domain | poonam | 1. registered new domain vishthamspm.in hosting remaining | in progress | 50%
other | poonam | 1.discus with atul,reena madam & dinesh sir how to implement next stage online exam.com | ___ | ___
Udise | ketan | 1.Recovery password Application 2.Work on DAR teacher Syntax | 1.Completed 2.In Progress | 1.100% 2.98%
myct.in | ketan | Work on teacher Syntax Ascii report | in progress | 98%
NSS | Padmaraj | worked on nss hierarchy, solved errors | in progress | 50%
Online Exam | Atul | 1. Add field medium in table subject and topic and change database , And field Class_Code in Add new class menu 2. Discuss with mam, Dinesh sir ,rina mam about online exam project | 1. completed | 1. 100%
Create web pages | praveen kumar | Create paid test page,sample test add content's project web pages link to each pages then heiglighted the colors some of the area of the page.Resole the cross browser issues. | in progress | 60%
SchoolApp | Vikas | Test and Correction | in progress | 75%
Daily Status Report 6th Aug, 2013
Project Name | Developer Name | Task Description | Current Status | Completion Perc.(%)
myct.in | poonam | 1 .upload Aurangabad HM List. 2. Upload Deulgao raja Teacher list & HM List. 3. Modify Add juniors Coding. | 1/2 completed 3.in progress | 1/2 - 100% 3- 40%
other | poonam | 1. solve college dropdown list displya tooltip problem with help raj patil 2. demo to raj,atul & ketan how to create hirarchy with 11 reference ,how to create ref ,How to create tree diagram. | completed | 100%
Online Exam | Atul | 1. separate sample test page (StartTest page and Sample Test page) using multiview and use master page 2. learn how to assign role , menu Explain by Poonam mam | 1. completed 2. completed | 1. 100% 2. 100%
udisecce | Ketan | 1.Checking Teacher Add list 2. DAR Report And Upload | 1/2 In progress | 95%
myct.in | ketan | 1.Work On UDISE Menu and add menu on HM Site, EO Site, And Super admin site | In progress | 90%
NSS | Padmaraj | Hierarchy and NSS Deactive Work | In progress | 80%
Grid view demo | Vikas | Worked on Grid view demo | In progress | 80%
Create new web pages | praveen kumar | Create web pages based on the competitive ,online exam. | In progress | 60%
Daily Status Report 5th Aug, 2013
Project Name | Developer Name | Task Description | Current Status | Completion Perc.(%)
Create web pages | praveen kumar | Create IBPS,MPSC,live project web pages link to each pages then heiglighted the colors some of the area of the pages and add some content. | in progress | 60%
myct.in | poonam | 1. check upload jalana & Sraja HM List on local machin & check tree diagram is correct or not . 2 . Upload jalana techar list on local machin check is proper upload or not with 11 reference. 3. test tree digrame with HM Login. 4. Add techer Active status in teacher master & testing on local side 5. upload jalana & Sraja HM List & jalana Techer list On server. | in progress | 98%
Udisecce | Ketan | Work On Teacher tree in Dar with Class Registration | in progress | 95%
myct.in | Ketan | Work on Asccii code Teacher Tree with Registration | in progress | 95%
ActionBar | Vikas | worked on ActionBar Demo | in progress | 90%
Online Exam | Atul | search solution to upload excel file and create demo application | in progress | 90%
myct.in | Atul | change all password of ezeesoft user name of both file local page and server page | completed | 100%
Daily Status Report 3st Aug, 2013
Project Name | Developer Name | Task Description | Current Status | Completion Perc.(%)
myct.in | poonam | 1.completed hirarchi structure with 11 stages reference. 2.check on local database. Check add or not reference &.3 check old reference replace or not.4. solve dummy no problem. 5.testing remaining on server | in progress | 95%
myct.in | Ketan | 1. Ascii Report Work 2. add 3rd Flag status of test table | in progress | 90%
Udisecce | ketan | 1.Work On Keyword with Hirarchy | in progress | 70%
Online Exam | Atul | 1. add master page design by praveen and add new page payment .aspx 2. add class ddl in add question page and solve error | 1. completed 2. inprogress | 1. 100% 2. 70%
Create web pages | praveen kumar | Create payment,MPSC,link to each pages then heiglighted the colors some of the area of the pages. | in progress | 60%
Member App | Vikas | Complete with XMl Parsing | completed | 100%
Nss | Padmaraj | Worked on NSS | completed | 95%
Daily Status Report 2st Aug, 2013
Project Name | Developer Name | Task Description | Current Status | Completion Perc.(%)
myct.in | poonam | 1. create new function add 11 stage reffrence new user. 2. testing HM & teacher reference add or not . 3. if you change any no. in tree then replace old reference to new reference. 4. testing reference replace or Not. | in progress | 75%
myct.in | Ketan | Add Keyword Send SMS Page 2. Work On ASCII DAR Report | in Progress | 60%
UDICCE | Ketan | Work On STUDENT attendence Teachar | inProgress | 95%
Online Exam | Atul | add class field in question page and add one master page design by praveen apply in project | completed | 100%
myct.in | Atul | ASCII dal report sorting | completed | 100%
MemberApp | Vikas | Applied new Changes | completed | 100%
1.Create New layout | praveen kumar | create new layout for Dinesh sir using photshop and some related images ,HTML5,CSS3. About US,Sample test,Paid test,Payment pages. | in progress | 60%
NSS | Padmaraj | user and admin, uploaded pune college list | in progress | 90%
Daily Status Report 1st Aug, 2013
Project Name | Developer Name | Task Description | Current Status | Completion Perc.(%)
myct.in | poonam | 1. Check registered all user under perticular role then fetch problem registered user not add in proper tree & not add his reference. 2. check where this problem fetch. 3. discus with sir how to add dummy reference in 11 stage & then check how to change old code & how to add new correction 4. Replace Hm Upload List Function & Tecaher Upload List Function On Teacher upload & Hm Upload Page. | in progress | 60%
other | poonam | 1. Download ezeesoft current project . Get july month Work Backup . | completed | 100%
Myct | ketan | 1. Testing Of DAR Syntax 2. Check ASSCI Format | 2.In progress | 2. 90%
UDISECCE | Ketan | 1. Work on SMS Report 2. Student Presenty 3.Teachar presenty | in progress | 90%
Online Exam | Atul | 1. do changes in project assign by Rina mam 2. add class field in topic menu and and apply validation create demo of excel upload in database | 1. Inprogress 2. inprogress | 1. 60% 2. 90%
MemberApp | vikas | Worked on XmlParsing | in progress | 50%
NSS & UDISE | Padamaraj | worked on NSS Admin and errors, ezeesoft india | in progress | 80%
Create New layout | praveen kumar | create new layout for Dinesh sir using photshop and some related images ,HTML5,CSS3. | in progress | 70%